Guidelines for Project Management 304 (PM 304), Engineering Honours Project 401/402 (EPH401/402), Engineering Project 401/402 (EP 401/402) and Computer Technology Project  391/392 (CTP 391/392).

These guidelines are to serve as a suggested schedule for the successful completion of the Engineering Project units (PM 304, EHP 401/402, EP 401/402, CTP 391/392)  which you will complete as part of your Bachelor’s degree. The schedule identifies the milestones and tasks to be completed in the project units and provides a time frame for the completion of the tasks.

Project Management 304

- Students who will be enrolling in the first project units will  select their projects in semester 2 the  year prior to starting the first project unit. Projects will be posted on the Project Noticeboard by the first week of  September. Students will select their project topic by week  10 of the semester.

(2) 	Projects will be categorised as Honours or Pass with selection for honours based on a course weighted average over the first 5 semesters of the Bachelor of Engineering course.  Students who qualify to do an Honours project will enrol in EHP 401/402  but may choose a Pass project which will exclude them from obtaining an Honours degree. Students completing a Pass project will enrol in EP 401/402 which may be undertaken in groups of up to three students.  Students enrolled in a Pass  project undertaken as a group will submit one joint thesis and any member of the group may be expected to present the seminar on the project. Students enrolled in a Pass project will be given a Pass/Fail grade.

(3) 	Conduct a feasibility study and finalise your project plan clearly identifying the milestones of the project by week 14. It is recommended that you confer and meet with your supervisor on a regular basis.

(4)	 Order all necessary components after conferring with the supervisor, to avoid delays for prototype development and testing in the next project unit. (Before the University closes for Christmas)

Engineering Honours Project  401, Engineering Project  401, Computer Technology Project 391.

(1) 	Implement project plan developed in the unit Project Management 304, complete prototype implementation and testing. (Week 1 - 13)

(2)	 Submit progress report to your supervisor for assessment. Submission to the School Main Office is to be before 4.00 p.m. on the last Friday of May. (Week 14)

Assessment: - You will be given a pass/fail mark for your project plan and progress report at this stage.

NOTE: - 	Student to meet/contact supervisor at least once per week; failure to meet/contact on two consecutive weeks may result in Fail grade. A letter from the School requesting a meeting between 	project coordinator, supervisor and student, will  be sent to you with  the outcome noted on the student’s  file.

Engineering Honours Project  402, Engineering Project  402, Computer Technology Project 392.

(1) 	Refine prototype  and complete writing thesis. (Week 1 - 8)

(2) 	Seminar preparation. Submit draft thesis for supervisor’s comments.  Order project folders.         (Week 9 -10)

(3) 	Seminar presentation. Seminar should be prepared using  Power point.

Seminars will be scheduled during the week free from classes .(Week 10).

(4) 	Two bound hard copies of thesis and one copy of thesis on disk in Microsoft Word or pdf  format to be handed to the School Main office before 4.00 p.m.  on the last Friday in October. ( Week 14). The use of the official Curtin binder is optional for the second hard copy of the thesis.

NOTE:- the disks must be virus free and should have stored on it a copy of your thesis in Microsoft Word  or pdf  format.

Assessment: -	Engineering Honours Project Thesis and Computer Technology Thesis    85% (Presentation 30%, Technical content  30%, Initiative/Originality 25%)

Seminar     15% (Presentation 50%, Technical content  50%)

Pass Thesis Pass/Fail grade

Seminar  Pass/Fail grade (If project is a group project a student from the group will be randomly selected to present the seminar).

NOTE: - 	Student to meet/contact the supervisor at least once per week; failure to meet/contact the supervisor on two consecutive weeks may result in a Fail grade. A letter from the School requesting a meeting between the project coordinator, supervisor and student,  will  be sent to you with the outcome noted on the student’s  file.

An Engineering Honours Project  Thesis and Computer Technology Thesis will be examined by the supervisor and one independent examiner who will be nominated by the supervisor to the Head of Department (HOD). Assessment by the co-examiner for the categories of Technical Content and Innovation/Initiative is optional. If the two results differ by more than 10 % the HOD to appoint a third examiner. Should the third examiner’s result vary by more than 10% when compared to the other two examiners results, the three results will be averaged to obtain the final result. Two or more theses from each Department ( 1 upper-band and 1 mid-band)  to be selected and examined by the Head of School (HOS) and examining panel as a basis of scaling marks across the three Departments. The examining panel is to be convened by the HOS. All theses with final results of 80% or higher are to be presented to the examining panel for selection of awards and prizes.

Pass  theses will be examined by the supervisor and one independent examiner that will be selected by the supervisor.  The result submitted will be a Pass or Fail and should there be no agreement between the two examiners the HOD will appoint a third examiner who will make an independent  assessment. Agreement of two out of the three examiners will be the final result.

Seminars will be judged on a departmental basis by all academic members of the Department. The seminars will be scheduled on Week  10 of the semester when no classes will be scheduled for 4th. year B.Eng. and final year Computer Technology students. The best two presenters from each 	Department to give a seminar in a combined School seminar program. These seminars 	will be judged by the HOS together with two invited adjudicators during week 11. The ratings from the combined seminar program will be used to scale departmental seminar scores.

Seminars will be concurrently scheduled in adjacent venues commencing on the Wednesday of the seminar week. Each HOD will be responsible for organising a chairperson and the rostering of staff for one venue. Attendance is compulsory for 2 half-day sessions for all third and fourth year students.

WJN 16299